## Sheet1
Risk ID | Category | Risk Description | Probability | Impact | Risk Score | Mitigation Strategy | Indicator | Contingency Plan | Responsible | Status | Last modifed date
1 | Technical | Engine update | 4 | 7 | 30 | - | Game doesn´t work as expected | Update the code | whole group | Open | 2023-04-13
2 | Project | Time schedule not well | 2 | 8 | 15 | plan less features; add them if there is enough time left | time is running out | reschedule the time plan, cut some planned features | whole group | Open | 2023-04-13
3 | Technical | Performance changes | 2 | 8 | 20 | pay attention how you code; some algorithms are faster then other | Game performance varies | Locate the affected code and try to fix it | whole group | Open | 2023-04-19
4 | Technical | Security risk | 1 | 6 | 10 | pay attention how you code; don´t leave backdoors open which potentially be used to cheat | Some cheating stratagies are published | Locate the affected code and try to fix it | whole group | Open | 2023-04-19